## Main
Tasks | Date | [17 empty] | Date | [17 empty] | Date
 | time axis 2025-11-20 to 2026-01-09
Initial meeting with client | bar: 2025-11-20
Define project scope and objectives | bar: 2025-11-22
Identify stakeholders and project team | bar: 2025-11-23
Create Gantt chart | bar: 2025-11-24
Client meeting – design discussion | bar: 2025-12-04
Create potential designs | bar: 2025-12-06 to 2025-12-10
Develop early prototype | bar: 2025-12-06 to 2025-12-08
Client review meeting | bar: 2025-12-11
Complete project plan (sign-off) | bar: 2025-12-12 to 2025-12-18
Client progress review | bar: 2025-12-18
Develop MVP / final prototype | bar: 2025-12-18 to 2025-12-31
Complete personal reflection | bar: 2026-01-01 to 2026-01-09
Tasks | 2025-11-20: Start Date; 2025-11-21: End Date
Initial meeting with client | 2025-11-20: 2025-11-20; 2025-11-21: 2025-11-20
Define project scope and objectives | 2025-11-20: 2025-11-22; 2025-11-21: 2025-11-22
Identify stakeholders and project team | 2025-11-20: 2025-11-23; 2025-11-21: 2025-11-23
Create Gantt chart | 2025-11-20: 2025-11-24; 2025-11-21: 2025-11-24
Client meeting – design discussion | 2025-11-20: 2025-12-04; 2025-11-21: 2025-12-04
Create potential designs | 2025-11-20: 2025-12-06; 2025-11-21: 2025-12-10
Develop early prototype | 2025-11-20: 2025-12-06; 2025-11-21: 2025-12-08
Client review meeting | 2025-11-20: 2025-12-11; 2025-11-21: 2025-12-11
Complete project plan (sign-off) | 2025-11-20: 2025-12-12; 2025-11-21: 2025-12-18
Client progress review | 2025-11-20: 2025-12-18; 2025-11-21: 2025-12-18
Develop MVP / final prototype | 2025-11-20: 2025-12-18; 2025-11-21: 2025-12-31
Complete personal reflection | 2025-11-20: 2026-01-01; 2025-11-21: 2026-01-09